## Submittal Register
TITLE: |  |  |  | AIMS McM Site & Utilities | [7 empty] | SUBMITTAL REGISTER
JOB NAME:
LOCATION:
CONTRACT NO:
CONTRACTOR:
[9 empty] | CONTRACTOR SCHEDULE DATES |  |  | CONTRACTOR ACTION |  |  | APPROVING AUTHORITY
| (a) | (b) | (c) | (d) |  |  | (e) | (f) | (g) | (h) | (i) | (j) | (k) | (l) | (m) | (n) | (o) | (p) | (q) | (r)
Line | Activity # | Trans-mittal # | Specification Section | SD # | Submittal Description | Item Submitted | Paragraph # | Classification: GOVT or A/E Revwr | Submit | Approval Needed By | Material Needed By | Action Code | Date Of Action | Date FWD to APPR / Auth Date RCD From CONTR | Date FWD To Other Revwr | Date RCD From Other Revwr | Action Code | Date Of Action | Mailed To CONTR/ Date RCD From APPR Authority | Remarks
1 |  |  | 01 91 00.15 | 01 | Preconstruction Submittals | Commissioning Firm | (e): 1.19
2 |  |  | 01 91 00.15 | 01 | Preconstruction Submittals | Lead Commissioning Specialist | (e): 1.19.1
3 |  |  | 01 91 00.15 | 01 | Preconstruction Submittals | Technical Commissioning Specialists | (e): 1.19.2
4 |  |  | 01 91 00.15 | 01 | Preconstruction Submittals | Commissioning Firm's Contract | (e): 1.19
5 |  |  | 01 91 00.15 | 05 | Design Data | Design Phase Commissioning Plan | (e): 3.1.2
6 |  |  | 01 91 00.15 | 06 | Test Reports | Design Review Report | (e): 3.1.3
7 |  |  | 01 91 00.15 | 06 | Test Reports | Design Review Report | (e): 3.2.3
8 |  |  | 01 91 00.15 | 06 | Test Reports | Interim Construction Phase Commissioning Plan | (e): 3.2.2.1
9 |  |  | 01 91 00.15 | 06 | Test Reports | Final Construction Phase Commissioning Plan | (e): 3.2.2.2
10 |  |  | 01 91 00.15 | 06 | Test Reports | Pre-Functional Checklists | (e): 3.2.5.3
11 |  |  | 01 91 00.15 | 06 | Test Reports | Issues Log | (e): 1.21
12 |  |  | 01 91 00.15 | 06 | Test Reports | Commissioning Report | (e): 3.15
13 |  |  | 01 91 00.15 | 07 | Certificates | Certificate of Readiness | (e): 1.22
14 |  |  | 01 91 00.15 | 10 | Operation and Maintenance Data | Training Plan | (e): 3.2.6
15 |  |  | 01 91 00.15 | 10 | Operation and Maintenance Data | Training Attendance Rosters | (e): 3.2.6
16 |  |  | 01 91 00.15 | 10 | Operation and Maintenance Data | Systems Manual | (e): 3.2.8
17 |  |  | 01 91 00.15 | 10 | Operation and Maintenance Data | Maintenance and Service Life Plans | (e): 3.2.9
18 |  |  | 01 91 00.15 | 11 | Closeout Submittals | Construction Phase Commissioning Plan | (e): 3.2.2.1
19 |  |  | 01 91 00.15 | 11 | Closeout Submittals | Final Commissioning Report | (e): 3.15
20 |  |  | 02 41 00 | 01 | Preconstruction Submittals | Demolition Plan | (e): 1.2.1
21 |  |  | 02 41 00 | 01 | Preconstruction Submittals | Existing Conditions | (e): 1.9
22 |  |  | 02 41 00 | 07 | Certificates | Notification | (e): 1.6
23 |  |  | 03 42 13.00 10 | 01 | Preconstruction Submittals | Quality Control Procedures | (e): 1.3.1.2
24 |  |  | 03 42 13.00 10 | 02 | Shop Drawings | Standard Precast Units | (e): 2.1.1
25 |  |  | 03 42 13.00 10 | 02 | Shop Drawings | Custom-Made Precast Units | (e): 2.1.2
26 |  |  | 03 42 13.00 10 | 03 | Product Data | Standard Precast Units | (e): 2.1.1
27 |  |  | 03 42 13.00 10 | 03 | Product Data | Proprietary Precast Units | (e): 2.1.3
28 |  |  | 03 42 13.00 10 | 03 | Product Data | Embedded Items | (e): 3.1.3
29 |  |  | 03 42 13.00 10 | 03 | Product Data | Accessories | (e): 2.2.6
30 |  |  | 03 42 13.00 10 | 05 | Design Data | Design Calculations | (e): 2.1.2
31 |  |  | 03 42 13.00 10 | 05 | Design Data | Concrete Mix Proportions | (e): 2.1.5.1
32 |  |  | 03 42 13.00 10 | 06 | Test Reports | Test Reports | (e): 1.3.1.4
33 |  |  | 03 42 13.00 10 | 07 | Certificates | Quality Control Procedures | (e): 1.3.1.2
34 |  |  | 03 42 13.00 10 | 11 | Closeout Submittals | Recycled content for fly ash and pozzolan | (e): 2.2.1
35 |  |  | 03 42 13.00 10 | 11 | Closeout Submittals | Recycled content for Ground Iron Blast-Furnace Slag | (e): 2.2.1
36 |  |  | 03 42 13.00 10 | 11 | Closeout Submittals | Recycled content for Silica Fume | (e): 2.2.1
37 |  |  | 03 42 13.00 10 | 11 | Closeout Submittals | Recycled content for Synthetic Fiber Reinforcement | (e): 2.2.1
38 |  |  | 03 42 13.00 10 | 11 | Closeout Submittals | Recycled content for steel | (e): 2.2.1
39 |  |  | 03 45 33 | 03 | Product Data | Inserts | (e): 2.1.1.1
40 |  |  | 03 45 33 | 05 | Design Data | Concrete Mix Design | (e): 1.4.3
41 |  |  | 03 45 33 | 06 | Test Reports | Concrete Mix Design | (e): 1.4.3
42 |  |  | 03 45 33 | 07 | Certificates | Quality Control Procedures | (e): 2.3
43 |  |  | 03 45 33 | 11 | Closeout Submittals | Batch Ticket | (e): 1.4.4
44 |  |  | 05 05 23.16 | 01 | Preconstruction Submittals | Welding Quality Assurance Plan | (e): 3.2
45 |  |  | 05 05 23.16 | 03 | Product Data | Welding Procedure Qualifications | (e): 1.3
46 |  |  | 05 05 23.16 | 03 | Product Data | Welder, Welding Operator, and Tacker Qualification | (e): 1.3.4
47 |  |  | 05 05 23.16 | 03 | Product Data | Inspector Qualification | (e): 1.3.5
48 |  |  | 05 05 23.16 | 03 | Product Data | Previous Qualifications | (e): 1.3.1
49 |  |  | 05 05 23.16 | 03 | Product Data | Pre-Qualified Procedures | (e): 1.3.2
50 |  |  | 05 05 23.16 | 03 | Product Data | Welding Electrodes and Rods | (e): 2.2
51 |  |  | 05 05 23.16 | 06 | Test Reports | Nondestructive Testing | (e): 3.3
52 |  |  | 05 12 00 | 01 | Preconstruction Submittals | Erection Drawings | (e): 1.3.1.1
53 |  |  | 05 12 00 | 02 | Shop Drawings | Fabrication Drawings | (e): 1.3.2
54 |  |  | 05 12 00 | 03 | Product Data | Shop Primer | (e): 2.6.2
55 |  |  | 05 12 00 | 03 | Product Data | Tension Control Bolts | (e): 2.3.3
56 |  |  | 05 12 00 | 06 | Test Reports | Bolts, Nuts, and Washers | (e): 2.3
57 |  |  | 05 12 00 | 06 | Test Reports | Weld Inspection Reports | (e): 3.7.1.2
58 |  |  | 05 12 00 | 07 | Certificates | Steel | (e): 2.2
59 |  |  | 05 12 00 | 07 | Certificates | Bolts, Nuts, and Washers | (e): 2.3
60 |  |  | 05 12 00 | 07 | Certificates | Galvanizing | (e): 2.5
61 |  |  | 05 12 00 | 07 | Certificates | Welding Procedures and Qualifications | (e): 1.3.3.1
62 |  |  | 05 50 13 | 02 | Shop Drawings | Floor Gratings | (e): 2.3
63 |  |  | 05 50 13 | 02 | Shop Drawings | Angles and Plates | (e): 2.4
64 |  |  | 05 51 00 | 02 | Shop Drawings | Steel Shapes, Plates, Bars and Strips | (e): 2.1
65 |  |  | 05 51 00 | 02 | Shop Drawings | Metal Stair System | (e): 2.9
66 |  |  | 05 51 00 | 03 | Product Data | Structural Steel Plates, Shapes, and Bars | (e): 2.2
67 |  |  | 05 51 00 | 03 | Product Data | Structural Steel Tubing | (e): 2.3
68 |  |  | 05 51 00 | 03 | Product Data | Hot-Rolled Carbon Steel Sheets and Strips | (e): 2.5
69 |  |  | 05 51 00 | 03 | Product Data | Galvanized Carbon Steel Sheets | (e): 2.6
70 |  |  | 05 51 00 | 03 | Product Data | Protective Coating | (e): 2.10
71 |  |  | 05 51 00 | 03 | Product Data | Steel Stairs | (e): 2.11.6
72 |  |  | 06 10 00 | 02 | Shop Drawings | Tank Timber Foundation | (e): 1.6.1
73 |  |  | 06 10 00 | 02 | Shop Drawings | Fabricated Structural Members | (e): 1.6.1
74 |  |  | 06 10 00 | 07 | Certificates | Certificates of Grade | (e): 1.7.1
75 |  |  | 07 27 39 | 03 | Product Data | Sprayed Polyurethane Foam Insulation | (e): 2.2
76 |  |  | 07 27 39 | 07 | Certificates | Installer Qualifications | (e): 1.3.1
77 |  |  | 07 27 39 | 07 | Certificates | Compatibility of Materials | (e): 1.3.3
78 |  |  | 07 27 39 | 08 | Manufacturer’s Instructions | Installation Instructions | (e): 1.3.4
79 |  |  | 07 27 39 | 08 | Manufacturer’s Instructions | Installation Instructions | (e): 1.4.1
80 |  |  | 07 27 39 | 08 | Manufacturer’s Instructions | Installation Instructions | (e): 3.4.2
81 |  |  | 07 41 63 | 06 | Test Reports | Leakage Tests | (e): 3.4.1.2
82 |  |  | 07 41 63 | 11 | Closeout Submittals | Warranty | (e): 1.7
83 |  |  | 07 41 63 | 11 | Closeout Submittals | Information Form and Placard | (e): 3.3.5
84 |  |  | 07 41 63 | 11 | Closeout Submittals | 20-year 'No-Dollar-Limit' Warranty for Labor and Materials | (e): 1.7.1
85 |  |  | 07 42 63 | 01 | Preconstruction Submittals | Qualification of Manufacturer | (e): 1.5.3
86 |  |  | 07 42 63 | 01 | Preconstruction Submittals | Qualification of Installer | (e): 1.5.4
87 |  |  | 07 42 63 | 01 | Preconstruction Submittals | Qualifications for Welding Work | (e): 1.5.4.1
88 |  |  | 07 42 63 | 02 | Shop Drawings | Fabrication and Installation drawings | (e): 1.5.1
89 |  |  | 07 42 63 | 02 | Shop Drawings | Wall Panel Assemblies | (e): 1.5.1
90 |  |  | 07 42 63 | 02 | Shop Drawings | Flashing and Accessories | (e): 1.5.1
91 |  |  | 07 42 63 | 02 | Shop Drawings | Anchorage Systems | (e): 1.5.1
92 |  |  | 07 42 63 | 03 | Product Data | sustainable acquisition | (e): 1.5.1
93 |  |  | 07 42 63 | 03 | Product Data | Manufacturer's catalog data | (e): 1.5.1
94 |  |  | 07 42 63 | 03 | Product Data | Factory Color Finish | (e): 1.5.1
95 |  |  | 07 42 63 | 03 | Product Data | Sub-girts and Formed Shapes | (e): 1.5.1
96 |  |  | 07 42 63 | 03 | Product Data | Closure Materials | (e): 1.5.1
97 |  |  | 07 42 63 | 03 | Product Data | Insulation | (e): 1.5.1
98 |  |  | 07 42 63 | 03 | Product Data | Pressure Sensitive Tape | (e): 1.5.1
99 |  |  | 07 42 63 | 03 | Product Data | Sealants and Caulking | (e): 2.4.4.1
100 |  |  | 07 42 63 | 03 | Product Data | Rated Wall Assembly | (e): 1.5.1
101 |  |  | 07 42 63 | 03 | Product Data | Galvanizing Repair Paint | (e): 1.5.1
102 |  |  | 07 42 63 | 03 | Product Data | Accessories | (e): 1.5.1
103 |  |  | 07 42 63 | 04 | Samples | Wall Panel Assemblies | (e): 1.5.1
104 |  |  | 07 42 63 | 04 | Samples | Fasteners | (e): 1.5.1
105 |  |  | 07 42 63 | 04 | Samples | Metal Closure Strips | (e): 1.5.1
106 |  |  | 07 42 63 | 04 | Samples | Insulation | (e): 1.5.1
107 |  |  | 07 42 63 | 04 | Samples | manufacturer's color charts and chips | (e): 1.5.1
108 |  |  | 07 42 63 | 05 | Design Data | Wind design analysis | (e): 1.5.1
109 |  |  | 07 42 63 | 06 | Test Reports | Leakage Tests | (e): 3.7.2
110 |  |  | 07 42 63 | 06 | Test Reports | Wind load tests | (e): 1.3.2
111 |  |  | 07 42 63 | 06 | Test Reports | seismic tests | (e): 1.3.2
112 |  |  | 07 42 63 | 06 | Test Reports | Factory Color Finish | (e): 1.5.1
113 |  |  | 07 42 63 | 07 | Certificates | Fasteners | (e): 1.5.1
114 |  |  | 07 42 63 | 07 | Certificates | Galvanizing Repair Paint | (e): 1.5.1
115 |  |  | 07 42 63 | 07 | Certificates | Qualification of Manufacturer | (e): 1.5.3
116 |  |  | 07 42 63 | 07 | Certificates | Qualification of Installer | (e): 1.5.4
117 |  |  | 07 42 63 | 07 | Certificates | wall system assembly wind load and fire rating classification listings | (e): 1.5.1
118 |  |  | 07 42 63 | 08 | Manufacturer’s Instructions | Installation of Wall panels | (e): 1.5.1
119 |  |  | 07 42 63 | 11 | Closeout Submittals | Instructions | (e): 1.5.1
120 |  |  | 07 42 63 | 11 | Closeout Submittals | Material Safety Data Sheets | (e): 1.5.1
121 |  |  | 07 42 63 | 11 | Closeout Submittals | 20 year 'No-Dollar-Limit' warranty | (e): 1.5.1
122 |  |  | 07 60 00 | 02 | Shop Drawings | Covering on flat, sloped surfaces | (e): 3.1.13
123 |  |  | 07 60 00 | 02 | Shop Drawings | Base flashing | (e): 3.1.10
124 |  |  | 07 60 00 | 02 | Shop Drawings | Counterflashing | (e): 3.1.11
125 |  |  | 07 92 00 | 03 | Product Data | Sealants | (e): 2.2
126 |  |  | 07 92 00 | 11 | Closeout Submittals | Indoor Air Quality For Interior Sealants | (e): 2.2.1
127 |  |  | 07 92 00 | 11 | Closeout Submittals | Indoor Air Quality For Interior Floor Joint Sealants | (e): 2.2.3
128 |  |  | 08 11 13 | 02 | Shop Drawings | Doors | (e): 2.1
129 |  |  | 08 11 13 | 02 | Shop Drawings | Doors | (e): 2.1
130 |  |  | 08 11 13 | 02 | Shop Drawings | Frames | (e): 2.4
131 |  |  | 08 11 13 | 02 | Shop Drawings | Frames | (e): 2.4
132 |  |  | 08 11 13 | 02 | Shop Drawings | Weatherstripping | (e): 2.5
133 |  |  | 08 11 13 | 03 | Product Data | Doors | (e): 2.1
134 |  |  | 08 11 13 | 03 | Product Data | Frames | (e): 2.4
135 |  |  | 08 11 13 | 03 | Product Data | Weatherstripping | (e): 2.5
136 |  |  | 08 71 00 | 02 | Shop Drawings | Manufacturer's Detail Drawings | (e): 1.3
137 |  |  | 08 71 00 | 02 | Shop Drawings | Verification of Existing Conditions | (e): 1.3
138 |  |  | 08 71 00 | 02 | Shop Drawings | Hardware Schedule | (e): 1.4
139 |  |  | 08 71 00 | 02 | Shop Drawings | Keying System | (e): 2.2.4
140 |  |  | 08 71 00 | 03 | Product Data | Hardware Items | (e): 2.2
141 |  |  | 08 71 00 | 08 | Manufacturer’s Instructions | Installation | (e): 3.1
142 |  |  | 08 71 00 | 10 | Operation and Maintenance Data | Hardware Schedule | (e): 1.4
143 |  |  | 08 71 00 | 11 | Closeout Submittals | Key Bitting | (e): 1.5.1
144 |  |  | 08 91 00 | 02 | Shop Drawings | Wall louvers | (e): 1.4
145 |  |  | 08 91 00 | 02 | Shop Drawings | Wall louvers | (e): 1.5
146 |  |  | 08 91 00 | 03 | Product Data | Metal Wall Louvers | (e): 2.2
147 |  |  | 08 91 00 | 04 | Samples | Wall louvers | (e): 1.4
148 |  |  | 08 91 00 | 04 | Samples | Wall louvers | (e): 1.5
149 |  |  | 08 91 00 | 04 | Samples | Door louvers | (e): 1.5
150 |  |  | 13 34 19 | 01 | Preconstruction Submittals | Manufacturer's Qualifications | (e): 1.6.3
151 |  |  | 13 34 19 | 02 | Shop Drawings | Detail Drawings | (e): 1.2.1.7
152 |  |  | 13 34 19 | 02 | Shop Drawings | Detail Drawings | (e): 1.6.1
153 |  |  | 13 34 19 | 03 | Product Data | Manufacturer's catalog data | (e): 1.6.1
154 |  |  | 13 34 19 | 05 | Design Data | descriptive and technical literature | (e): 1.6.1
155 |  |  | 13 34 19 | 05 | Design Data | building design analysis | (e): 1.6.1
156 |  |  | 13 34 19 | 06 | Test Reports | test reports | (e): 1.6.1
157 |  |  | 13 34 19 | 06 | Test Reports | Coatings and base metals | (e): 1.6.1
158 |  |  | 13 34 19 | 06 | Test Reports | Factory Color Finish Performance Requirements | (e): 1.6.1
159 |  |  | 13 34 19 | 07 | Certificates | system components | (e): 1.6.1
160 |  |  | 13 34 19 | 07 | Certificates | Coil Stock | (e): 1.6.1
161 |  |  | 13 34 19 | 07 | Certificates | Coil Stock | (e): 2.1.5
162 |  |  | 13 34 19 | 07 | Certificates | Qualification of Manufacturer | (e): 1.6.1
163 |  |  | 13 34 19 | 07 | Certificates | Qualification of Erector | (e): 1.6.1
164 |  |  | 13 34 19 | 08 | Manufacturer’s Instructions | shipping, handling, and storage | (e): 1.7
165 |  |  | 13 34 19 | 11 | Closeout Submittals | Manufacturer's Warranty | (e): 3.11.1
166 |  |  | 22 00 00 | 07 | Certificates | Materials and Equipment | (e): 1.3
167 |  |  | 22 00 00 | 07 | Certificates | Bolts | (e): 2.1.1
168 |  |  | 23 00 00 | 02 | Shop Drawings | Detail Drawings | (e): 1.4.3
169 |  |  | 23 00 00 | 03 | Product Data | Duct Access Doors | (e): 2.9.2
170 |  |  | 23 00 00 | 03 | Product Data | Diffusers | (e): 2.9.7.1
171 |  |  | 23 00 00 | 03 | Product Data | Registers and Grilles | (e): 2.9.7.2
172 |  |  | 23 00 00 | 03 | Product Data | Louvers | (e): 2.9.8
173 |  |  | 23 00 00 | 03 | Product Data | Energy Recovery Devices | (e): 2.11
174 |  |  | 23 00 00 | 03 | Product Data | Diagrams | (e): 1.2.1.2
175 |  |  | 23 00 00 | 06 | Test Reports | Performance Tests | (e): 3.11
176 |  |  | 23 00 00 | 06 | Test Reports | Damper Acceptance Test | (e): 3.9
177 |  |  | 23 00 00 | 08 | Manufacturer’s Instructions | Manufacturer's Installation Instructions | (e): 3.2
178 |  |  | 23 00 00 | 08 | Manufacturer’s Instructions | Operation and Maintenance Training | (e): 3.13.2
179 |  |  | 23 00 00 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.13.1
180 |  |  | 23 00 00 | 10 | Operation and Maintenance Data | Energy Recovery Devices | (e): 2.11
181 |  |  | 23 05 15 | 01 | Preconstruction Submittals | Material, Equipment, and Fixture Lists | (e): 1.2
182 |  |  | 23 05 15 | 02 | Shop Drawings | Record Drawings | (e): 1.2
183 |  |  | 23 05 15 | 02 | Shop Drawings | Connection Diagrams | (e): 1.2
184 |  |  | 23 05 15 | 02 | Shop Drawings | Coordination Drawings | (e): 1.2
185 |  |  | 23 05 15 | 02 | Shop Drawings | Fabrication Drawings | (e): 1.2
186 |  |  | 23 05 15 | 02 | Shop Drawings | Installation Drawings | (e): 3.1
187 |  |  | 23 05 15 | 03 | Product Data | Pipe and Fittings | (e): 2.3
188 |  |  | 23 05 15 | 03 | Product Data | Piping Specialties | (e): 2.4
189 |  |  | 23 05 15 | 03 | Product Data | Valves | (e): 2.5
190 |  |  | 23 05 15 | 03 | Product Data | Miscellaneous Materials | (e): 2.6
191 |  |  | 23 05 15 | 03 | Product Data | Supporting Elements | (e): 2.7
192 |  |  | 23 05 15 | 03 | Product Data | Equipment Foundation Data | (e): 1.2
193 |  |  | 23 05 15 | 04 | Samples | Manufacturer's Standard Color Charts | (e): 1.2
194 |  |  | 23 05 15 | 05 | Design Data | Pipe and Fittings | (e): 2.3
195 |  |  | 23 05 15 | 05 | Design Data | Piping Specialties | (e): 2.4
196 |  |  | 23 05 15 | 05 | Design Data | Valves | (e): 2.5
197 |  |  | 23 05 15 | 06 | Test Reports | Hydrostatic Tests | (e): 3.1
198 |  |  | 23 05 15 | 06 | Test Reports | Air Tests | (e): 3.1
199 |  |  | 23 05 15 | 06 | Test Reports | Valve-Operating Tests | (e): 3.1
200 |  |  | 23 05 15 | 06 | Test Reports | Non-Destructive Electric Tests | (e): 3.1
201 |  |  | 23 05 15 | 06 | Test Reports | System Operation Tests | (e): 3.1
202 |  |  | 23 05 15 | 07 | Certificates | Record of Satisfactory Field Operation | (e): 1.4.2
203 |  |  | 23 05 15 | 07 | Certificates | List of Qualified Permanent Service Organizations | (e): 1.4.3
204 |  |  | 23 05 15 | 07 | Certificates | Listing of Product Installations | (e): 1.2
205 |  |  | 23 05 15 | 07 | Certificates | Records of Existing Conditions | (e): 1.2
206 |  |  | 23 05 15 | 07 | Certificates | Surface Resistance | (e): 3.1
207 |  |  | 23 05 15 | 07 | Certificates | Shear and Tensile Strengths | (e): 3.1
208 |  |  | 23 05 15 | 07 | Certificates | Temperature Ratings | (e): 3.1
209 |  |  | 23 05 15 | 07 | Certificates | Bending Tests | (e): 3.1
210 |  |  | 23 05 15 | 07 | Certificates | Flattening Tests | (e): 3.1
211 |  |  | 23 05 15 | 07 | Certificates | Transverse Guided Weld Bend Tests | (e): 3.1
212 |  |  | 23 05 15 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.12
213 |  |  | 23 05 93 | 01 | Preconstruction Submittals | Records of Existing Conditions | (e): 1.3.3
214 |  |  | 23 05 93 | 01 | Preconstruction Submittals | Records of Existing Conditions | (e): 1.3.3
215 |  |  | 23 05 93 | 01 | Preconstruction Submittals | Independent TAB Agency and Personnel Qualifications | (e): 1.5.1
216 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Design Review Report | (e): 1.6.2.1
217 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Firm | (e): 1.5.8.1
218 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Team Assistants | (e): 1.2
219 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Team Engineer | (e): 1.2
220 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Specialist | (e): 1.5.8.2
221 |  |  | 23 05 93 | 01 | Preconstruction Submittals | TAB Team Field Leader | (e): 1.2
222 |  |  | 23 05 93 | 02 | Shop Drawings | TAB Schematic Drawings and Report Forms | (e): 1.3.3
223 |  |  | 23 05 93 | 03 | Product Data | Equipment and Performance Data | (e): 1.3
224 |  |  | 23 05 93 | 03 | Product Data | TAB Related HVAC Submittals | (e): 1.5.1.3
225 |  |  | 23 05 93 | 03 | Product Data | TAB Related HVAC Submittals | (e): 1.5.8.4
226 |  |  | 23 05 93 | 03 | Product Data | TAB Procedures | (e): 1.5.6
227 |  |  | 23 05 93 | 03 | Product Data | Calibration | (e): 1.5.6
228 |  |  | 23 05 93 | 03 | Product Data | Systems Readiness Check | (e): 1.3.3
229 |  |  | 23 05 93 | 03 | Product Data | TAB Execution | (e): 1.5.9
230 |  |  | 23 05 93 | 06 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.5.4.3
231 |  |  | 23 05 93 | 06 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.5.4.3
232 |  |  | 23 05 93 | 06 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.6.2
233 |  |  | 23 05 93 | 06 | Test Reports | Prerequisite HVAC Work Checkout List | (e): 1.6.2
234 |  |  | 23 05 93 | 06 | Test Reports | Proportional Balancing | (e): 3.6
235 |  |  | 23 05 93 | 07 | Certificates | Independent TAB Agency and Personnel Qualifications | (e): 1.5.1
236 |  |  | 23 05 93 | 07 | Certificates | TAB Submittal and Work Schedule | (e): 1.5.4.2
237 |  |  | 23 05 93 | 07 | Certificates | TAB Submittal and Work Schedule | (e): 1.6.2
238 |  |  | 23 05 93 | 07 | Certificates | TAB Pre-Field Engineering Report | (e): 1.5.4.3
239 |  |  | 23 05 93 | 07 | Certificates | TAB Pre-Field Engineering Report | (e): 1.6.2.2
240 |  |  | 23 05 93 | 07 | Certificates | Instrument Calibration Certificates | (e): 1.5.5
241 |  |  | 23 05 93 | 07 | Certificates | TAB Procedures Summary | (e): 3.6
242 |  |  | 23 05 93 | 07 | Certificates | Proportional Balancing | (e): 3.6
243 |  |  | 23 05 93 | 07 | Certificates | TAB Firm | (e): 1.5.8.1
244 |  |  | 23 05 93 | 07 | Certificates | Design Review Report | (e): 1.3.3
245 |  |  | 23 07 00 | 02 | Shop Drawings | Pipe Insulation Systems | (e): 2.3
246 |  |  | 23 07 00 | 02 | Shop Drawings | Pipe Insulation Systems | (e): 3.2
247 |  |  | 23 07 00 | 02 | Shop Drawings | Duct Insulation Systems | (e): 3.3
248 |  |  | 23 07 00 | 02 | Shop Drawings | Equipment Insulation Systems | (e): 3.4
249 |  |  | 23 07 00 | 03 | Product Data | Pipe Insulation Systems | (e): 2.3
250 |  |  | 23 07 00 | 03 | Product Data | Pipe Insulation Systems | (e): 3.2
251 |  |  | 23 07 00 | 03 | Product Data | Duct Insulation Systems | (e): 3.3
252 |  |  | 23 07 00 | 03 | Product Data | Equipment Insulation Systems | (e): 3.4
253 |  |  | 23 07 00 | 04 | Samples | Thermal Insulation | (e): 2.2.1.3
254 |  |  | 23 07 00 | 04 | Samples | Display Samples | (e): 3.1.1
255 |  |  | 23 07 00 | 08 | Manufacturer’s Instructions | Pipe Insulation Systems | (e): 2.3
256 |  |  | 23 07 00 | 08 | Manufacturer’s Instructions | Pipe Insulation Systems | (e): 3.2
257 |  |  | 23 07 00 | 08 | Manufacturer’s Instructions | Duct Insulation Systems | (e): 3.3
258 |  |  | 23 07 00 | 08 | Manufacturer’s Instructions | Equipment Insulation Systems | (e): 3.4
259 |  |  | 23 09 00 | 02 | Shop Drawings | DDC Contractor Design Drawings | (e): 3.2
260 |  |  | 23 09 00 | 02 | Shop Drawings | Draft As-Built Drawings | (e): 3.2
261 |  |  | 23 09 00 | 02 | Shop Drawings | Final As-Built Drawings | (e): 3.2
262 |  |  | 23 09 00 | 03 | Product Data | Programming Software | (e): 1.8.3
263 |  |  | 23 09 00 | 03 | Product Data | Controller Application Programs | (e): 1.8.4
264 |  |  | 23 09 00 | 03 | Product Data | Configuration Software | (e): 1.8.1
265 |  |  | 23 09 00 | 03 | Product Data | Controller Configuration Settings | (e): 1.8.2
266 |  |  | 23 09 00 | 03 | Product Data | Manufacturer's Product Data | (e): 2.2
267 |  |  | 23 09 00 | 06 | Test Reports | Start-Up Testing Report | (e): 3.4.2
268 |  |  | 23 09 00 | 06 | Test Reports | PVT Procedures | (e): 3.5.1
269 |  |  | 23 09 00 | 06 | Test Reports | PVT Report | (e): 3.5.3
270 |  |  | 23 09 00 | 06 | Test Reports | Pre-Construction Quality Control (QC) Checklist | (e): 1.9.1
271 |  |  | 23 09 00 | 06 | Test Reports | Post-Construction Quality Control (QC) Checklist | (e): 1.9.2
272 |  |  | 23 09 00 | 10 | Operation and Maintenance Data | Operation and Maintenance (O&M) Instructions | (e): 3.6
273 |  |  | 23 09 00 | 10 | Operation and Maintenance Data | Training Documentation | (e): 3.7.1
274 |  |  | 23 09 00 | 11 | Closeout Submittals | Enclosure Keys | (e): 2.5
275 |  |  | 23 09 00 | 11 | Closeout Submittals | Password Summary Report | (e): 3.1.6.1
276 |  |  | 23 09 00 | 11 | Closeout Submittals | Closeout Quality Control (QC) Checklist | (e): 1.9.3
277 |  |  | 26 05 13.00 40 | 03 | Product Data | Multiple-Conductor Shielded Cables | (e): 2.2.1
278 |  |  | 26 05 13.00 40 | 06 | Test Reports | Dielectric-Absorption Tests | (e): 3.2
279 |  |  | 26 05 13.00 40 | 06 | Test Reports | Medium-Voltage Tests | (e): 3.2
280 |  |  | 26 05 13.00 40 | 06 | Test Reports | Radiographic Tests | (e): 3.2
281 |  |  | 26 05 13.00 40 | 07 | Certificates | Flammability | (e): 2.5
282 |  |  | 26 05 13.00 40 | 07 | Certificates | Minimum Bending Radius | (e): 3.1.2
283 |  |  | 26 05 13.00 40 | 07 | Certificates | Medium-Voltage Tests | (e): 3.2
284 |  |  | 26 05 13.00 40 | 07 | Certificates | Dielectric Absorption Tests | (e): 3.2
285 |  |  | 26 05 13.00 40 | 07 | Certificates | Cable Splicers | (e): 1.4
286 |  |  | 26 05 13.00 40 | 08 | Manufacturer’s Instructions | Medium-Voltage Power Cables | (e): 3.3
287 |  |  | 26 05 13.00 40 | 08 | Manufacturer’s Instructions | Pothead Terminations | (e): 3.3
288 |  |  | 26 12 19.00 40 | 02 | Shop Drawings | Transformer Drawings | (e): 1.4.1
289 |  |  | 26 12 19.00 40 | 03 | Product Data | Transformers | (e): 1.5.1
290 |  |  | 26 12 19.00 40 | 03 | Product Data | Transformers | (e): 2.1.1
291 |  |  | 26 12 19.00 40 | 06 | Test Reports | Acceptance Checks And Tests | (e): 3.3.1
292 |  |  | 26 12 19.00 40 | 07 | Certificates | Transformer Losses | (e): 2.1.1.5
293 |  |  | 26 12 19.00 40 | 09 | Manufacturer’s Field Reports | Design Tests | (e): 2.3.2
294 |  |  | 26 12 19.00 40 | 09 | Manufacturer’s Field Reports | Routine and Other Tests | (e): 2.3.3
295 |  |  | 26 12 19.00 40 | 10 | Operation and Maintenance Data | Transformer(s) | (e): 1.5.1
296 |  |  | 26 12 19.00 40 | 10 | Operation and Maintenance Data | Transformer(s) | (e): 2.1.1
297 |  |  | 26 12 19.00 40 | 11 | Closeout Submittals | Transformer Test Schedule | (e): 2.3.1
298 |  |  | 26 12 19.00 40 | 11 | Closeout Submittals | Warranty | (e): 1.6
299 |  |  | 26 13 01 | 02 | Shop Drawings | Switchgear Drawings | (e): 1.4.1
300 |  |  | 26 13 01 | 03 | Product Data | Fuse Time-Current Characteristic Curves | (e): 1.4.3
301 |  |  | 26 13 01 | 03 | Product Data | Air Insulated Switchgear | (e): 2.1
302 |  |  | 26 13 01 | 03 | Product Data | Insulated High-Voltage Connectors | (e): 2.2
303 |  |  | 26 13 01 | 03 | Product Data | Surge Arresters | (e): 2.3
304 |  |  | 26 13 01 | 06 | Test Reports | Acceptance Checks and Tests | (e): 3.4.1
305 |  |  | 26 13 01 | 07 | Certificates | Paint Coating System | (e): 1.4.2
306 |  |  | 26 13 01 | 09 | Manufacturer’s Field Reports | Switchgear design and production tests | (e): 2.6.1
307 |  |  | 26 13 01 | 10 | Operation and Maintenance Data | Air Insulated Switchgear Operation and Maintenance | (e): 1.5.1
308 |  |  | 26 18 23.00 40 | 03 | Product Data | Equipment and Performance Data | (e): Part 2
309 |  |  | 26 18 23.00 40 | 03 | Product Data | Mounting Brackets | (e): 2.1.3
310 |  |  | 26 18 23.00 40 | 08 | Manufacturer’s Instructions | Installation Instructions | (e): 3.1.1
311 |  |  | 26 18 23.00 40 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.2
312 |  |  | 26 20 00 | 02 | Shop Drawings | Panelboards | (e): 2.11
313 |  |  | 26 20 00 | 02 | Shop Drawings | Cable trays | (e): 2.3
314 |  |  | 26 20 00 | 03 | Product Data | Receptacles | (e): 2.10
315 |  |  | 26 20 00 | 03 | Product Data | Circuit breakers | (e): 2.11.3
316 |  |  | 26 20 00 | 03 | Product Data | Switches | (e): 2.9
317 |  |  | 26 20 00 | 03 | Product Data | Grounding Busbar | (e): 2.17.1
318 |  |  | 26 20 00 | 03 | Product Data | Surge protective devices | (e): 2.21
319 |  |  | 26 20 00 | 06 | Test Reports | 600-volt wiring test | (e): 3.5.2
320 |  |  | 26 20 00 | 06 | Test Reports | Grounding system test | (e): 3.5.4
321 |  |  | 26 20 00 | 06 | Test Reports | Ground-fault receptacle test | (e): 3.5.3
322 |  |  | 26 20 00 | 10 | Operation and Maintenance Data | Electrical Systems | (e): 1.5.1
323 |  |  | 26 27 13.10 30 | 03 | Product Data | Power Meters | (e): 2.1
324 |  |  | 26 27 13.10 30 | 03 | Product Data | Current | (e): 2.1.3
325 |  |  | 26 27 13.10 30 | 03 | Product Data | Potential Transformer | (e): 2.1.2
326 |  |  | 26 27 13.10 30 | 03 | Product Data | Communications Module | (e): 2.2.2
327 |  |  | 26 27 13.10 30 | 03 | Product Data | Protocol Modules | (e): 1.6.1
328 |  |  | 26 27 13.10 30 | 03 | Product Data | Data Recorder | (e): 1.6.2
329 |  |  | 26 27 13.10 30 | 03 | Product Data | Modem | (e): 1.6.2
330 |  |  | 26 27 13.10 30 | 06 | Test Reports | Acceptance Checks and Tests | (e): 3.3.1
331 |  |  | 26 27 13.10 30 | 10 | Operation and Maintenance Data | Power Meters | (e): 2.1
332 |  |  | 26 27 13.10 30 | 10 | Operation and Maintenance Data | Communications Module | (e): 2.2.2
333 |  |  | 26 27 13.10 30 | 10 | Operation and Maintenance Data | Protocol Modules | (e): 1.6.1
334 |  |  | 26 27 13.10 30 | 10 | Operation and Maintenance Data | Data Recorder | (e): 1.6.2
335 |  |  | 26 27 13.10 30 | 10 | Operation and Maintenance Data | Modem | (e): 1.6.2
336 |  |  | 26 27 13.10 30 | 11 | Closeout Submittals | System Function Verification | (e): 3.3.2
337 |  |  | 26 28 01.00 10 | 03 | Product Data | Fault Current Analysis | (e): 2.12
338 |  |  | 26 28 01.00 10 | 03 | Product Data | Protective Device Coordination Study | (e): 2.12
339 |  |  | 26 28 01.00 10 | 03 | Product Data | Equipment | (e): 2.1
340 |  |  | 26 28 01.00 10 | 03 | Product Data | System Coordinator | (e): 1.4.1
341 |  |  | 26 28 01.00 10 | 03 | Product Data | Installation | (e): 3.2
342 |  |  | 26 28 01.00 10 | 06 | Test Reports | Field Testing | (e): 3.3
343 |  |  | 26 28 01.00 10 | 07 | Certificates | Devices and Equipment | (e): 1.6
344 |  |  | 26 29 23 | 02 | Shop Drawings | Schematic diagrams | (e): 1.5.1
345 |  |  | 26 29 23 | 02 | Shop Drawings | Interconnecting diagrams | (e): 1.5.2
346 |  |  | 26 29 23 | 02 | Shop Drawings | Installation drawings | (e): 1.5.3
347 |  |  | 26 29 23 | 03 | Product Data | Variable frequency drives | (e): 2.1
348 |  |  | 26 29 23 | 03 | Product Data | Wires and cables | (e): 2.3
349 |  |  | 26 29 23 | 03 | Product Data | Equipment schedule | (e): 1.5.4
350 |  |  | 26 29 23 | 06 | Test Reports | VFD Test | (e): 3.2.1
351 |  |  | 26 29 23 | 06 | Test Reports | Performance Verification Tests | (e): 3.2.2
352 |  |  | 26 29 23 | 06 | Test Reports | Endurance Test | (e): 3.2.3
353 |  |  | 26 29 23 | 08 | Manufacturer’s Instructions | Installation instructions | (e): 1.5.5
354 |  |  | 26 29 23 | 10 | Operation and Maintenance Data | Variable frequency drives | (e): 2.1
355 |  |  | 27 05 28.36 40 | 02 | Shop Drawings | Installation Drawings | (e): 3.1.2
356 |  |  | 27 05 28.36 40 | 03 | Product Data | Cable Trays | (e): 1.2.1
357 |  |  | 27 05 28.36 40 | 03 | Product Data | Supports | (e): 1.2.1
358 |  |  | 27 05 28.36 40 | 08 | Manufacturer’s Instructions | Manufacturer's Instructions | (e): 3.1.1
359 |  |  | 27 10 00 | 03 | Product Data | Telecommunications cabling | (e): 2.3
360 |  |  | 27 10 00 | 03 | Product Data | Patch panels | (e): 2.4.5
361 |  |  | 27 10 00 | 03 | Product Data | Equipment support frame | (e): 2.4.2
362 |  |  | 27 10 00 | 03 | Product Data | Connector blocks | (e): 2.4.3
363 |  |  | 27 10 00 | 03 | Product Data | Spare Parts | (e): 1.10.3
364 |  |  | 27 10 00 | 06 | Test Reports | Telecommunications cabling testing | (e): 3.5.1
365 |  |  | 27 10 00 | 07 | Certificates | Telecommunications Contractor | (e): 1.6.1.1
366 |  |  | 27 10 00 | 07 | Certificates | Key Personnel | (e): 1.6.1.2
367 |  |  | 27 10 00 | 07 | Certificates | Manufacturer Qualifications | (e): 1.6.1.3
368 |  |  | 27 10 00 | 07 | Certificates | Test plan | (e): 1.6.2
369 |  |  | 27 10 00 | 09 | Manufacturer’s Field Reports | Factory reel tests | (e): 2.8.1
370 |  |  | 27 10 00 | 10 | Operation and Maintenance Data | Telecommunications cabling and pathway system | (e): 1.10.1
371 |  |  | 27 10 00 | 11 | Closeout Submittals | Record Documentation | (e): 1.10.2
372 |  |  | 31 00 00 | 01 | Preconstruction Submittals | Shoring | (e): 3.4
373 |  |  | 31 00 00 | 01 | Preconstruction Submittals | Dewatering Work Plan | (e): 1.3.3
374 |  |  | 31 00 00 | 03 | Product Data | Utilization of Excavated Materials | (e): 3.7
375 |  |  | 31 00 00 | 03 | Product Data | Opening of any Excavation or Borrow Pit | (e): 3.3
376 |  |  | 31 00 00 | 06 | Test Reports | Testing | (e): 3.13
377 |  |  | 31 00 00 | 07 | Certificates | Testing | (e): 3.13
378 |  |  | 33 11 00 | 03 | Product Data | Pipe, Fittings, Joints and Couplings | (e): 2.2
379 |  |  | 33 11 00 | 03 | Product Data | Valves | (e): 2.3
380 |  |  | 33 11 00 | 03 | Product Data | Hydrants | (e): 2.4.1
381 |  |  | 33 11 00 | 06 | Test Reports | Bacteriological Samples | (e): 3.2.4
382 |  |  | 33 11 00 | 07 | Certificates | Pipe, Fittings, Joints and Couplings | (e): 2.2
383 |  |  | 33 11 00 | 07 | Certificates | Valves | (e): 2.3
384 |  |  | 33 11 00 | 07 | Certificates | Disinfection Procedures | (e): 3.2.4
385 |  |  | 33 11 00 | 08 | Manufacturer’s Instructions | Manufacturer's Instructions | (e): 3.2.1
386 |  |  | 33 16 15 | 02 | Shop Drawings | Design Calculations | (e): 2.1
387 |  |  | 33 16 15 | 02 | Shop Drawings | Design Calculations | (e): 2.1
388 |  |  | 33 16 15 | 02 | Shop Drawings | Tank Fabrication and Installation | (e): 3.3
389 |  |  | 33 16 15 | 02 | Shop Drawings | Welded Joint | (e): 3.3
390 |  |  | 33 16 15 | 02 | Shop Drawings | Anchorage | (e): 2.1.1
391 |  |  | 33 16 15 | 02 | Shop Drawings | Foundation Design | (e): 2.1.3
392 |  |  | 33 16 15 | 03 | Product Data | Insulation System | (e): 2.3.1.4
393 |  |  | 33 16 15 | 03 | Product Data | Insulation System | (e): 2.3.3
394 |  |  | 33 16 15 | 03 | Product Data | Coating System | (e): 2.4.1
395 |  |  | 33 16 15 | 03 | Product Data | System Description | (e): 2.1
396 |  |  | 33 16 15 | 03 | Product Data | Foundations | (e): 3.1
397 |  |  | 33 16 15 | 06 | Test Reports | Mill Test Reports | (e): 3.4.2
398 |  |  | 33 16 15 | 06 | Test Reports | Mill and Shop Inspection | (e): 3.3.3
399 |  |  | 33 16 15 | 06 | Test Reports | Mill and Shop Inspection | (e): 3.4.2
400 |  |  | 33 16 15 | 06 | Test Reports | Tank Installation | (e): 3.3
401 |  |  | 33 16 15 | 06 | Test Reports | Testing of Valves and Piping | (e): 3.4.2
402 |  |  | 33 16 15 | 06 | Test Reports | Welder Qualifications | (e): 2.1.2
403 |  |  | 33 16 15 | 06 | Test Reports | Welding Procedure Specifications | (e): 2.1.2
404 |  |  | 33 16 15 | 07 | Certificates | System Description | (e): 2.1
405 |  |  | 33 16 15 | 07 | Certificates | Foundations | (e): 3.1
406 |  |  | 33 16 15 | 07 | Certificates | Coatings Certification | (e): 2.1.5
407 |  |  | 33 16 15 | 07 | Certificates | Inspection | (e): 3.8
408 |  |  | 33 30 00 | 01 | Preconstruction Submittals | Existing Conditions | (e): 1.6
409 |  |  | 33 30 00 | 02 | Shop Drawings | Drawings | (e): 1.4.2
410 |  |  | 33 30 00 | 03 | Product Data | Pipeline Materials | (e): 2.1
411 |  |  | 33 30 00 | 06 | Test Reports | Reports | (e): 2.2
412 |  |  | 33 30 00 | 07 | Certificates | Post-Construction Inspection | (e): 3.2.2
413 |  |  | 33 40 00 | 03 | Product Data | Placing Pipe | (e): 3.3
414 |  |  | 33 52 43 | 03 | Product Data | Gate Valve | (e): 2.5.2
415 |  |  | 33 52 43 | 06 | Test Reports | Preliminary Pneumatic Test | (e): 3.2.1.1
416 |  |  | 33 52 43 | 06 | Test Reports | Final Pneumatic Test | (e): 3.2.1.2
417 |  |  | 33 52 43 | 06 | Test Reports | Hydrostatic Test | (e): 3.2.1.3
418 |  |  | 33 52 43 | 07 | Certificates | Contractor Qualifications | (e): 1.4.2
419 |  |  | 33 52 43 | 07 | Certificates | Licensed Personnel | (e): 1.7
420 |  |  | 33 52 43 | 10 | Operation and Maintenance Data | Gate Valve | (e): 2.5.2
421 |  |  | 33 61 14 | 02 | Shop Drawings | Factory-prefabricated preinsulated piping system | (e): 2.1
422 |  |  | 33 61 14 | 02 | Shop Drawings | field joints | (e): 3.2
423 |  |  | 33 61 14 | 03 | Product Data | Pipe, fittings, and end connections | (e): 2.1
424 |  |  | 33 61 14 | 03 | Product Data | Factory-prefabricated preinsulated piping system | (e): 2.1
425 |  |  | 33 61 14 | 07 | Certificates | Certification of welders' qualifications | (e): 1.4.1
426 |  |  | 33 61 14 | 08 | Manufacturer’s Instructions | factory-prefabricated preinsulated piping system | (e): 2.1
427 |  |  | 33 71 02 | 03 | Product Data | Medium voltage cable | (e): 2.5
428 |  |  | 33 71 02 | 03 | Product Data | Medium voltage cable terminations | (e): 2.6
429 |  |  | 33 71 02 | 03 | Product Data | Protective Devices and Coordination | (e): 2.15
430 |  |  | 33 71 02 | 06 | Test Reports | Medium voltage cable qualification and production tests | (e): 2.16.1
431 |  |  | 33 71 02 | 06 | Test Reports | Field Acceptance Checks and Tests | (e): 3.12.1
432 |  |  | 33 71 02 | 07 | Certificates | Cable splicer/terminator | (e): 1.5.1
433 |  |  | 33 71 02 | 07 | Certificates | Cable Installer Qualifications | (e): 1.5.2
434 |  |  | 33 82 00 | 03 | Product Data | Wire and cable | (e): 2.6
435 |  |  | 33 82 00 | 03 | Product Data | Building protector assemblies | (e): 2.2.1
436 |  |  | 33 82 00 | 03 | Product Data | Protector modules | (e): 2.2.2
437 |  |  | 33 82 00 | 03 | Product Data | Spare Parts | (e): 1.8.2
438 |  |  | 33 82 00 | 06 | Test Reports | Pre-installation tests | (e): 3.5.1
439 |  |  | 33 82 00 | 06 | Test Reports | Acceptance tests | (e): 3.5.2
440 |  |  | 33 82 00 | 06 | Test Reports | Outside Plant Test Plan | (e): 1.6.2
441 |  |  | 33 82 00 | 07 | Certificates | Telecommunications Contractor | (e): 1.6.1.1
442 |  |  | 33 82 00 | 07 | Certificates | Key Personnel | (e): 1.6.1.2
443 |  |  | 33 82 00 | 07 | Certificates | Manufacturer's Qualifications | (e): 1.6.1.3
444 |  |  | 33 82 00 | 08 | Manufacturer’s Instructions | Building protector assembly installation | (e): 2.2.1
445 |  |  | 33 82 00 | 08 | Manufacturer’s Instructions | Cable tensions | (e): 3.1.5.1
446 |  |  | 33 82 00 | 09 | Manufacturer’s Field Reports | Factory Reel Test Data | (e): 2.11.1
447 |  |  | 33 82 00 | 11 | Closeout Submittals | Record Documentation | (e): 1.8.1
448 |  |  | 43 21 13 | 02 | Shop Drawings | Installation | (e): 3.2
449 |  |  | 43 21 13 | 03 | Product Data | Materials and Equipment | (e): 2.2
450 |  |  | 43 21 13 | 03 | Product Data | Operating Instructions | (e): 3.2.2
451 |  |  | 43 21 13 | 03 | Product Data | Training Period | (e): 3.8.1
452 |  |  | 43 21 13 | 06 | Test Reports | Factory Performance Tests | (e): 2.9
453 |  |  | 43 21 13 | 06 | Test Reports | Field Tests | (e): 3.3
454 |  |  | 43 21 13 | 07 | Certificates | Manufacturer's Representative | (e): 1.4
455 |  |  | 43 21 13 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.8.1
456 |  |  | 43 21 13 | 10 | Operation and Maintenance Data | Operation and Maintenance Manuals | (e): 3.8.2
457 |  |  | 43 21 29 | 03 | Product Data | equipment | (e): 2.1
458 |  |  | 43 21 29 | 03 | Product Data | Read-out device | (e): 2.2
459 |  |  | 43 21 29 | 06 | Test Reports | calibration | (e): 3.2
460 |  |  | 43 21 29 | 08 | Manufacturer’s Instructions | equipment | (e): 2.1